## Project Plan and Budget
Electoral Commission Community Education Fund 2026 Project Plan and Risk Register Template
Organisation Name | Organisation ABC
Project Name | Community Education Hui |  |  | Example milestones, timeframes, resources, and budget amounts are in blue. Please delete these and provide your own milestones, timeframes, resources, and budget amounts
Project Lead | Xyz Xyz
Key Milestones | Timeframes | Resource Required | Budget Amount
Plan four community education hui | 1 June to 14 June | temporary coordinator salary | 1000
|  | Electoral Commission information resources | 0
|  | local advertisement | 2000
|  | lockable safe for enrolment forms | 200
Deliver Hui 1 | 2026-06-17 | temporary coordinator salary | 2000
|  | catering | 1000
|  | venue hire | 500
Deliver Hui 2 | 2026-07-01 | temporary coordinator salary | 2000
|  | catering | 1000
|  | venue hire | 1200
Deliver Hui 3 | 2026-07-15 | temporary coordinator salary | 2000
|  | catering | 1000
|  | venue hire | 200
Deliver Hui 4 | 2026-07-29 | temporary coordinator salary | 2000
|  | catering | 1000
|  | venue hire | 1400
Total Budget |  |  | 18500

## Risk Register
Organisation Name | Organisation ABC |  |  | Please give each risk a rating of Low/Medium/High, or Very High using the table below
Project Name | Community Education Hui |  |  | Please rate the bold political neutrality risk and provide a mitigation. Please also delete the blue example risks and replace with your own risks and mitigations. | example
Project Lead | Xyz Xyz
Identified Risk | Risk Rating (Likely, Feasible, Slight) | Mitigation | DRAFT
Our organisation is not able to maintain political neutrality | Medium | We will ensure that we work in a politically neutral way and will come to the Electoral Commission if we are unsure
We are unable to secure venues for all four hui and therefore unable to deliver our project | Low | Work early with trusted community venues to secure the necessary dates
There is low attendance at community hui and we do not reach the people we expect to reach | Medium | Advertise the hui widely amongst trusted community groups and in local publications
Community members attend hui but are not interested in checking which roll they are on or in discussing voting | Low | Provide easy ways to check enrolment status at the hui
Enrolment forms are lost and we are not able to support our community to enrol | High | We adhere to secure data handling procedures